## PMR 1ST SEM (hidden)
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | DepEd Regional Office VIII Procurement Monitoring Report as of January to June 2019
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Procurement of Supply of Door to Door Delivery of Athletic Uniform for the EVRAA Delegation to the Palarong Pambansa 2019 | [19 empty] | ESSD | NO | Competitive Bidding | NONE | NONE | Jan. 18, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Feb. 15, 2019 | Mar. 29, 2019 | Feb. 21, 2019 | Feb. 21, 2019 | Feb. 22, 2019 | April 26, 2019 | April 26, 2019 | GoP | 1530000 | 1529896.32 |  | 1529896.32 | 1529896.32 |  | 6 | Jan. 18, 2019 | Jan. 18, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Feb. 15, 2019 | N/A
2 | Procurement of Repair & Rehabilitation of NEAP RO8 Dormitory | [19 empty] | HRDD-NEAP | NO | Competitive Bidding | NONE | NONE | Mar 22, 2019 | April 3, 2019 | April 3, 2019 | April 3, 2019 | April 3, 2019 | April 30, 2019 | May 6, 2019 | May 10, 2019 | May 10, 2019 | July 8, 2019 |  | GoP | 2498195.78 | 2498195.78 |  | 2490411.18 | 2490411.18 |  | 5 | Mar 22, 2019 | April 3, 2019 | April 3, 2019 | April 3, 2019 | April 3, 2019 | N/A
3 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 3) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | Feb. 14, 2019 | Aug. 15, 2019 | Aug. 19, 2019 | Aug. 20, 2019 | Dec. 13, 2019 | Dec. 11,2019 | GoP | 15072000 |  | 15072000 | 15056190 |  | 15056190 | 5 | Dec. 19, 2018 | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | N/A
4 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 4) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | Feb. 14, 2019 | Aug. 15, 2019 | Aug. 19, 2019 | Aug. 20, 2019 |  |  | GoP | 24024000 |  | 24024000 | 23998800 |  | 23998800 | 5 | Dec. 20, 2018 | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | N/A
5 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 5) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 8, 2019 | Feb. 14, 2019 | Aug. 15, 2019 | Aug. 19, 2019 | Aug. 20, 2019 | Nov. 25, 2019 | Nov. 25, 2019 | GoP | 28056000 |  | 28056000 | 28026570 |  | 28026570 | 5 | Dec. 20, 2018 | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 8, 2019 | N/A
6 | Procurement of DepEd Regional Office No. VIII Repair and Rehabilitation | [19 empty] | ADMIN | NO | Competitive Bidding | NONE | NONE | May 29, 2019 | June 10, 2019 | June 10, 2019 | June 10, 2019 | June 11, 2019 | Jun. 19, 2019 | June 21, 2019 | June 26, 2019 | June 17, 2019 |  |  | GoP | 1899938.67 | 1899938.67 |  | 1877815.24 | 1877815.24 |  | 6 | May 29, 2019 | June 10, 2019 | June 10, 2019 | June 10, 2019 | June 11, 2019 | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 73080134.45
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 72979682.74
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 100451.71
0N-GOING PROCUREMENT ACTIVITIES
1 | Procurement for Hiring of Licensed Security Agency to Provide Eight (8) Guards, (Seven (7) Security Guards & 1 Head Guard) for DepEd RO8 for CY 2019 | [19 empty] | GSU | NO | Competitive Bidding | NONE | NONE | Jan 18. 2019 | Jan 31, 2019 | Jan 31, 2019 | Jan 31, 2019 | Feb. 15, 2019 | Feb. 19, 2019 | Feb. 21, 2019 | Feb. 21, 2019 | Feb. 22, 2019 | April 1, 2020 |  | GoP | 1530000 | 1530000 |  | 1529896.52 | 1529896.52 |  | 6 | Jan 18. 2019 | Jan 31, 2019 | Jan 31, 2019 | Jan 31, 2019 | Feb. 15, 2019 | N/A
2 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 1) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | Feb. 14, 2019 | Sept. 30, 2019 | Oct. 9, 2019 | Oct. 16, 2019 |  | April 3, 2020 | GoP | 23772800 |  | 23772800 | 20444129 |  | 20444129 | 6 | Dec. 19, 2018 | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | N/A
3 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 2) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | Feb. 14, 2019 | Sept. 30, 2019 | Oct. 9, 2019 | Oct. 16, 2019 |  |  | GoP | 24481600 |  | 24481600 | 24326901.62 |  | 24326901.62 | 6 | Dec. 19, 2018 | Dec. 19, 2018 | Jan. 3, 2019 | Jan. 3, 2019 | Jan. 4, 2019 | N/A
4 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 6) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | Feb. 14, 2019 | Sept. 30, 2019 | Oct. 9, 2019 | Oct. 16, 2019 |  |  | GoP | 27799200 |  | 27799200 | 27746720 |  | 27746720 | 5 | Dec. 20, 2018 | Dec. 20, 2018 | Jan. 4, 2019 | Jan. 4, 2019 | Jan. 4, 2019 | N/A
5 | Procurement for the Provision of School Furniture for CY 2019 (Cluster 7) | [19 empty] | ESSD | NO | Competitive Bidding | Dec. 10, 2018 | NONE | Jan. 18, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Feb. 8, 2019 | Feb. 14, 2019 | Aug. 26, 2019 | Sept. 2, 2019 | Sept. 9, 2019 |  |  | GoP | 25368000 |  | 25368000 | 25357800 |  | 25357800 | 5 | Jan. 18, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Jan. 31, 2019 | Feb. 8, 2019 | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 102951600

## PMR 2nd Sem 2024
|  | ANNEX A | [18 empty] | ANNEX B
Department of Education Regional Office VIII - 2024 PROCUREMENT MONITORING REPORT (PMR) FOR SECOND SEMESTER (JULY - DECEMBER 2024)
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Procurement of Mathematics Learning Resources (Manipulative Materials) | [19 empty] | CLMD-LRMS | NO | CB | 2024-03-06 | 3/21/2024 | 6/18/2024 | 2024-01-07 | 2024-01-07 | 2024-01-07 | 2024-11-07 | 2024-12-08 | 8/14/2024 | 8/19/2024 | 8/20/2024 | Completed | Inspected and Accepted | OSEC-8-23-6805 | 86498425 |  | 86498425 | 37966500 |  | 37966500 | COA, NEDA, GWATCH, PPSTA, PCCI | 6/18/2024 | 2024-01-07 | 2024-01-07 | 2024-01-07 | 2024-11-07 | Completed | NONE
2 | Procurement of Board and Lodging for the Regional Training of SHS-TVL and JHS-SPVTE Teachers on Trainers Methodology ™ Level 1 | [19 empty] | CLMD | NO | CB | 7/19/2024 | 7/19/2024 | 2024-08-08 | 8/22/2024 | 8/22/2024 | 8/22/2024 | 8/27/2024 | 8/28/2024 | 8/29/2024 | 8/30/2024 | 2024-02-09 | On-Going | On-Going | OSEC-8-24-0012 | 3412000 |  | 3412000 | 2947968 |  | 2947968 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-08-08 | 8/22/2024 | 8/22/2024 | 8/22/2024 | 8/27/2024 | On-Going | NONE
3 | Procurement of Board and Lodging for the Regional-Based Training of Multigrade School Heads and Supervisors | [19 empty] | CLMD | NO | CB | N/A | 2024-07-09 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-01-10 | 2024-02-10 | 2024-03-10 | 2024-05-10 | 2024-07-10 | Completed | Inspected and Accepted | 2024 MG (Current Fund) | 1450000 |  | 1450000 | 1226700 |  | 1226700 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-01-10 | Completed | NONE
4 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 4 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/24 | 7/31/2024 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-07-10 | 10/14/2024 | 10/17/2024 | 10/19/2024 | 10/21/2024 | On-Going | On-Going | OSEC-8-23-5880 | 412297.7 |  | 412297.7 | 412297.7 |  | 412297.7 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-07-10 | On-Going | NONE
5 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 5 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 7/31/2024 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-10-10 | 10/16/2024 | 10/18/2024 | 10/18/2024 | 10/28/2024 | On-Going | On-Going | OSEC-8-23-5880 | 3729269.68 |  | 3729269.68 | 3729269.68 |  | 3729269.68 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-10-10 | On-Going | NONE
6 | Procurement of Board and Lodging for the Regional Upskilling of English Teachers in Language Instruction | [19 empty] | CLMD-LRMS | NO | CB | N/A | 2024-12-10 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 10/21/2024 | 10/25/2024 | 10/28/2024 | 10/30/2024 | 2024-04-11 | Completed | Inspected and Accepted | OSEC-8-23-5065 | 1160000 |  | 1160000 | 1056760 |  | 1056760 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 10/21/2024 | Completed | NONE
7 | Procurement of Board and Lodging for the National Conference of Cashiers in the RO and SDOs and Selected Implementing Units | [19 empty] | ADMIN | NO | CB | 9/30/2024 | 2024-02-10 | 10/810/2024 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | 10/30/2024 | 10/31/2024 | 2024-05-11 | 2024-06-11 | Completed | Inspected and Accepted | OSEC-8-24-6257 | 2319000 |  | 2319000 | 3190320 |  | 3190320 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/810/2024 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | Completed | NONE
8 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 7 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 7/21/2024 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-05-11 | 2024-07-11 | 2024-08-11 | 2024-12-11 | 11/13/2024 | On-Going | On-Going | OSEC-8-24-2499 | 8968320 |  | 8968320 | 8968320 |  | 8968320 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-05-11 | On-Going | NONE
9 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 7 | [19 empty] | CLMD-LRMS | NO | CB | N/A | 2024-12-10 | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | 11/13/2024 | 11/15/2024 | 11/19/2024 | 11/20/2024 | On-Going | On-Going | OSEC-8-23-5880 | 816314 |  | 816314 | 816314 |  | 816314 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | On-Going | NONE
10 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 1 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 12/29/2024 | 2024-03-12 | 2024-05-12 | 2024-09-12 | On-Going | On-Going | OSEC-8-24-4050 | 15080000 |  | 15080000 | 15080000 |  | 15080000 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | On-Going | NONE
11 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 2 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 12/13/2024 | On-Going | On-Going | OSEC-8-24-4050 | 11306230 |  | 11306230 | 11306230 |  | 11306230 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | On-Going | NONE
12 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 3 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 | On-Going | On-Going | OSEC-8-24-4050 | 5609760 |  | 5609760 | 5591664 |  | 5591664 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | On-Going | NONE
13 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 1 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 12/13/2024 | On-Going | On-Going | OSEC-8-24-2499 | 9058560 |  | 9058560 | 9058560 |  | 9058560 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | On-Going | NONE
14 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 4 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 2024-12-12 | On-Going | On-Going | OSEC-8-24-2499 | 5760000 |  | 5760000 | 5760000 |  | 5760000 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | On-Going | NONE
15 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 5 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 | On-Going | On-Going | OSEC-8-24-2499 | 5017600 |  | 5017600 | 5017600 |  | 5017600 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | On-Going | NONE
16 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 6 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | 2024-09-12 | 2024-11-12 | 12/13/2024 | 12/16/2024 | On-Going | On-Going | OSEC-8-24-2499 | 8296320 |  | 8296320 | 8264960 |  | 8264960 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | On-Going | NONE
17 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 3 (Re-Bid) | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 2024-05-11 | 12/13/2024 | 12/26/2024 | 12/26/2024 | 12/26/2024 | 12/29/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 | On-Going | On-Going | OSEC-8-24-2499 | 2977958.4 |  | 2977958.4 | 2977958.4 |  | 2977958.4 | COA, NEDA, GWATCH, PPSTA, PCCI | 12/13/2024 | 12/26/2024 | 12/26/2024 | 12/26/2024 | 12/29/2024 | On-Going | NONE
18 | Procurement of Printing and Delivery of Storeybook Packages to 13 SDOs | [19 empty] | CLMD-LRMS | NO | CB | 9/16/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 10/21/2024 | 10/30/2024 | 2024-08-11 | 11/18/2024 | On-Going | On-Going | OSEC-8-24-4034 | 21655603.2 |  | 21655603.2 | 14888227.2 |  | 14888227.2 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A | On-Going | NONE
19 | Procurement of Printing and Delivery of K-FELT Grades 1-3 Learning Resources to 13 SDOs to Support the NLRP | [19 empty] | CLMD-LRMS | NO | CB | 9/16/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 10/31/2024 | 11/22/2024 | 11/29/2024 | 12/16/2024 | On-Going | On-Going | OSEC-8-23-3057 | 12283112.4 |  | 12283112.4 | 12283112.4 |  | 12283112.4 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A | On-Going | NONE
20 | Procurement of Additional Printing and Delivery of Storeybook Packages to 13 SDOs | [19 empty] | CLMD-LRMS | NO | CB | 9/13/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 11/25/2024 | 11/26/2024 | 11/29/2024 | 12/16/2024 | On-Going | On-Going | OSEC-8-24-4034 | 6568654.4 |  | 6568654.4 | 6568654.4 |  | 6568654.4 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A | On-Going | NONE
21 | Procurement of Additional Mathematics Learning Resources (Manipulative Materials) | [19 empty] | CLMD-LRMS | NO | CB | 11/13/2024 | 11/15/2024 | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 12/16/2024 | 12/18/2024 | 12/19/2024 | 12/20/2024 | 12/23/2024 | On-Going | On-Going | OSEC-8-23-6805 | 44001447.75 |  | 44001447.75 | 21956717.25 |  | 21956717.25 | COA, NEDA, GWATCH, PPSTA, PCCI | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 12/16/2024 | On-Going | NONE
22 | Procurement and Delivery of Tablets for ALS Learners at the School-Based Community Learning Centers (CLC) with no Computers in DepEd Region VIII | [19 empty] | CLMD-ALS | NO | CB | 11/13/2024 | 11/15/2024 | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-12-12 | 12/18/2024 | 12/19/2024 | 12/21/2024 | 12/23/2024 | On-Going | On-Going | OSEC-8-24-5794 | 20325000 |  | 20325000 | 14159750 |  | 14159750 | COA, NEDA, GWATCH, PPSTA, PCCI | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-12-12 | On-Going | NONE
23 | Procurement and Delivery of Tablets for Alternative Delivery Mode (ADM) Learners of DepEd Region VIII | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 12/18/2024 | 12/18/2024 | 12/19/2024 | 12/21/2024 | 12/21/2024 | On-Going | On-Going | OSEC-8-24-5778 | 5880000 |  | 5880000 | 5272400 |  | 5272400 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 12/18/2024 | On-Going | NONE
24 | Procurement of Board and Lodging for the Instructional Leadership Training (ILT): Strengthening Learning Conditions for Early Literacy | [19 empty] | CLMD | NO | CB | 10/21/2024 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/14/2024 | 11/15/2024 | 11/18/2024 | 11/19/2024 | 11/20/2024 | Completed | Inspected and Accepted | OSEC-8-24-1736 | 2904500 |  | 2904500 | 2787840 |  | 2787840 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/14/2024 | Completed | NONE
25 | Procurement of Supplementary Learning Resources (SLRs) for Library Hubs and Delivery to Eight (8) SDOs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tacloban) FY 2023-Lot 3 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 2024-01-12 | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/24/2024 | 12/26/2024 | 12/27/2024 | 12/31/2024 | On-Going | On-Going | OSEC-8-23-5880 | 2551111.09 |  | 2551111.09 | 2551111.09 |  | 2551111.09 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | On-Going | NONE
26 | Procurement of Supplementary Learning Resources (SLRs) for Library Hubs and Delivery to Eight (8) SDOs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tacloban) FY 2023-Lot 2 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 2024-01-12 | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/24/2024 | 12/26/2024 | 12/27/2024 | 12/31/2024 | On-Going | On-Going | OSEC-8-23-5645 | 420502 |  | 420502 | 420502 |  | 420502 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | On-Going | NONE
27 | Procurement for Emergency GO Bag Sets for DepEd Regional Office VIII Personnel | [19 empty] | ESSD | NO | CB | 2024-10-12 | 2024-03-12 | 2024-10-12 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/26/2024 | 12/27/2027 | 12/28/2024 | 12/31/2024 | On-Going | On-Going | OSEC-8-23-5645 | 2231515 |  | 2231515 | 1972838 |  | 1972838 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-12 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/24/2024 | On-Going | NONE
[33 empty] | Total Allotted Budget of Procurement Activities |  |  |  |  | 290693500.62 |  | 290693500.62
[33 empty] | Total Contract Price of Procurement Activities Conducted | [7 empty] | 206232574.12 |  | 206232574.12
[33 empty] | Total Savings (Total Allotted Budget - Total Contract Price) |  |  |  |  | 84460926.5
ON-GOING PROCUREMENT ACTIVITIES
1 | Procurement for the Hiring of a Licensed Security Agency to Provide Nine (9) Security Guards for Twelve (12) Months from April 2025 to March 2026 (EARLY PROCUREMENT ACTIVITY) | [19 empty] | ADMIN | YES | CB | 9/30/2024 | 2024-02-10 | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 2024-06-11 | 11/16/2024 | [5 empty] | RO GASS FUND | 2381147.25 | 104923000 |  | 2340274.68 | 2340274.68 |  | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 2024-06-11
2 | Production and Delivery of Grades 6 and 10 Q1 and Q2 SLMs to 13 SDOs (EARLY PROCUREMENT ACTIVITY) | [19 empty] | CLMD-LRMS | YES | AGENCY TO AGENCY | 9/30/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 11/26/2024 | [5 empty] | FY 2025 Directly Released Funds | 106537200 |  | 106537200 | 104923000 |  | 104923000 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A
3 | Procurement for the Production and Delivery of Math 1 Learning Activity Sheets (LAS) Q1-Q4 to (13 SDOs) | [19 empty] | CLMD-LRMS | NO | AGENCY TO AGENCY | 2024-10-12 | N/A | N/A | N/A | N/A | N/A | N/A | 12/18/2024 | 12/19/2024 | 12/27/2024 |  |  |  | OSEC-8-24-6604 | 3102778.8 |  | 3102778.8 | 3055067 |  | 3055067 |  | N/A | N/A | N/A | N/A | N/A
4 | Procurement of Printing and Delivery of English, Science, and Math Formative Assessment Sheets to 13 SDOs | [19 empty] | CLMD-LRMS | NO | AGENCY TO AGENCY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12/16/2024 | 12/19/2024 | 12/27/2024 |  |  |  | OSEC-8-23-3142 | 1567441.26 |  | 1567441.26 | 1543692.15 |  | 1543692.15 |  | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [38 empty] | 104923000 | 111207420.06 | 111862033.83 | 2340274.68 | 109521759.15
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by:
[21 empty] | RACHEL R. CUEVAS | [10 empty] | HARVIE D. VILLAMOR | [10 empty] | EVELYN R. FETALVERO, CESO III
[21 empty] | Head, BAC Secretariat | [10 empty] | Chief, HRDD | [10 empty] | Regional Director
[32 empty] | Chairperson- BAC | [8 empty] | Head of the Procuring Entity (HoPE)

## Working docs
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | DepEd Regional Office VIII Procurement Monitoring Report (PMR) as of July to December 2024 (2nd Semester)
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Procurement of Mathematics Learning Resources (Manipulative Materials) | [19 empty] | CLMD-LRMS | NO | CB | 2024-03-06 | 3/21/2024 | 6/18/2024 | 2024-01-07 | 2024-01-07 | 2024-01-07 | 2024-11-07 | 2024-12-08 | 8/14/2024 | 8/19/2024 | 8/20/2024 |  |  | OSEC-8-23-6805 | 86498425 |  | 86498425 | 37966500 |  | 37966500 | COA, NEDA, GWATCH, PPSTA, PCCI | 6/18/2024 | 2024-01-07 | 2024-01-07 | 2024-01-07 | 2024-11-07
2 | Procurement of Board and Lodging for the Regional Training of SHS-TVL and JHS-SPVTE Teachers on Trainers Methodology ™ Level 1 | [19 empty] | CLMD | NO | CB | 7/19/2024 | 7/19/2024 | 2024-08-08 | 8/22/2024 | 8/22/2024 | 8/22/2024 | 8/27/2024 | 8/28/2024 | 8/29/2024 | 8/30/2024 | 2024-02-09 |  |  | OSEC-8-24-0012 | 3412000 |  | 3412000 | 2947968 |  | 2947968 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-08-08 | 8/22/2024 | 8/22/2024 | 8/22/2024 | 8/27/2024
3 | Procurement of Board and Lodging for the Regional-Based Training of Multigrade School Heads and Supervisors | [19 empty] | CLMD | NO | CB | N/A | 2024-07-09 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-01-10 | 2024-02-10 | 2024-03-10 | 2024-05-10 | 2024-07-10 |  |  | 2024 MG (Current Fund) | 1450000 |  | 1450000 | 1226700 |  | 1226700 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-01-10
4 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 4 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/24 | 7/31/2024 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-07-10 | 10/14/2024 | 10/17/2024 | 10/19/2024 | 10/21/2024 |  |  | OSEC-8-23-5880 | 412297.7 |  | 412297.7 | 412297.7 |  | 412297.7 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-07-10
5 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 5 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 7/31/2024 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-10-10 | 10/16/2024 | 10/18/2024 | 10/18/2024 | 10/28/2024 |  |  | OSEC-8-23-5880 | 3729269.68 |  | 3729269.68 | 3729269.68 |  | 3729269.68 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 2024-10-10
6 | Procurement of Board and Lodging for the Regional Upskilling of English Teachers in Language Instruction | [19 empty] | CLMD-LRMS | NO | CB | N/A | 2024-12-10 | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 10/21/2024 | 10/25/2024 | 10/28/2024 | 10/30/2024 | 2024-04-11 |  |  | OSEC-8-23-5065 | 1160000 |  | 1160000 | 1056760 |  | 1056760 | COA, NEDA, GWATCH, PPSTA, PCCI | 9/16/2024 | 9/30/2024 | 9/30/2024 | 9/30/2024 | 10/21/2024
7 | Procurement of Board and Lodging for the National Conference of Cashiers in the RO and SDOs and Selected Implementing Units | [19 empty] | ADMIN | NO | CB | 9/30/2024 | 2024-02-10 | 10/810/2024 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | 10/30/2024 | 10/31/2024 | 2024-05-11 | 2024-06-11 |  |  | OSEC-8-24-6257 | 2319000 |  | 2319000 | 3190320 |  | 3190320 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/810/2024 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024
8 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 7 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 7/21/2024 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-05-11 | 2024-07-11 | 2024-08-11 | 2024-12-11 | 11/13/2024 |  |  | OSEC-8-24-2499 | 8968320 |  | 8968320 | 8968320 |  | 8968320 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-05-11
9 | Procurement of SLRs for the Library Hubs and Delivery to Eight (8) SDOs-Lot 7 | [19 empty] | CLMD-LRMS | NO | CB | N/A | 2024-12-10 | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024 | 11/13/2024 | 11/15/2024 | 11/19/2024 | 11/20/2024 |  |  | OSEC-8-23-5880 | 816314 |  | 816314 | 816314 |  | 816314 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 10/24/2024
10 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 1 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 12/29/2024 | 2024-03-12 | 2024-05-12 | 2024-09-12 |  |  | OSEC-8-24-4050 | 15080000 |  | 15080000 | 15080000 |  | 15080000 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024
11 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 2 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 12/13/2024 |  |  | OSEC-8-24-4050 | 11306230 |  | 11306230 | 11306230 |  | 11306230 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024
12 | Procurement for the Remediation Packages and Delivery for Reading Program to the Thriteen (13) SDOs of DepEd Region VIII-Lot 3 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 |  |  | OSEC-8-24-4050 | 5609760 |  | 5609760 | 5591664 |  | 5591664 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024
13 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 1 | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 10/23/2024 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 12/13/2024 |  |  | OSEC-8-24-2499 | 9058560 |  | 9058560 | 9058560 |  | 9058560 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024
14 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 4 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | 2024-06-12 | 2024-09-12 | 2024-11-12 | 2024-12-12 |  |  | OSEC-8-24-2499 | 5760000 |  | 5760000 | 5760000 |  | 5760000 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024
15 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 5 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 |  |  | OSEC-8-24-2499 | 5017600 |  | 5017600 | 5017600 |  | 5017600 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/13/2024
16 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 6 | [19 empty] | CLMD-LRMS | NO | CB | 10/21/2024 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024 | 2024-09-12 | 2024-11-12 | 12/13/2024 | 12/16/2024 |  |  | OSEC-8-24-2499 | 8296320 |  | 8296320 | 8264960 |  | 8264960 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 11/14/2024
17 | Procurement of Supplementary Learning Resources (SLRs) and Delivery for the Library Hubs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tac. City) CY 2024-Lot 3 (Re-Bid) | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 2024-05-11 | 12/13/2024 | 12/26/2024 | 12/26/2024 | 12/26/2024 | 12/29/2024 | 2024-11-12 | 12/13/2024 | 12/17/2024 | 12/18/2024 |  |  | OSEC-8-24-2499 | 2977958.4 |  | 2977958.4 | 2977958.4 |  | 2977958.4 | COA, NEDA, GWATCH, PPSTA, PCCI | 12/13/2024 | 12/26/2024 | 12/26/2024 | 12/26/2024 | 12/29/2024
18 | Procurement of Printing and Delivery of Storeybook Packages to 13 SDOs | [19 empty] | CLMD-LRMS | NO | CB | 9/16/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 10/21/2024 | 10/30/2024 | 2024-08-11 | 11/18/2024 |  |  | OSEC-8-24-4034 | 21655603.2 |  | 21655603.2 | 14888227.2 |  | 14888227.2 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A
19 | Procurement of Printing and Delivery of K-FELT Grades 1-3 Learning Resources to 13 SDOs to Support the NLRP | [19 empty] | CLMD-LRMS | NO | CB | 9/16/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 10/31/2024 | 11/22/2024 | 11/29/2024 | 12/16/2024 |  |  | OSEC-8-23-3057 | 12283112.4 |  | 12283112.4 | 12283112.4 |  | 12283112.4 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A
20 | Procurement of Additional Printing and Delivery of Storeybook Packages to 13 SDOs | [19 empty] | CLMD-LRMS | NO | CB | 9/13/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 11/25/2024 | 11/26/2024 | 11/29/2024 | 12/16/2024 |  |  | OSEC-8-24-4034 | 6568654.4 |  | 6568654.4 | 6568654.4 |  | 6568654.4 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A
21 | Procurement of Additional Mathematics Learning Resources (Manipulative Materials) | [19 empty] | CLMD-LRMS | NO | CB | 11/13/2024 | 11/15/2024 | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 12/16/2024 | 12/18/2024 | 12/19/2024 | 12/20/2024 | 12/23/2024 |  |  | OSEC-8-23-6805 | 44001447.75 |  | 44001447.75 | 21956717.25 |  | 21956717.25 | COA, NEDA, GWATCH, PPSTA, PCCI | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 12/16/2024
22 | Procurement and Delivery of Tablets for ALS Learners at the School-Based Community Learning Centers (CLC) with no Computers in DepEd Region VIII | [19 empty] | CLMD-ALS | NO | CB | 11/13/2024 | 11/15/2024 | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-12-12 | 12/18/2024 | 12/19/2024 | 12/21/2024 | 12/23/2024 |  |  | OSEC-8-24-5794 | 20325000 |  | 20325000 | 14159750 |  | 14159750 | COA, NEDA, GWATCH, PPSTA, PCCI | 11/26/2024 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-12-12
23 | Procurement and Delivery of Tablets for Alternative Delivery Mode (ADM) Learners of DepEd Region VIII | [19 empty] | CLMD-LRMS | NO | CB | 2024-10-10 | 2024-12-10 | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 12/18/2024 | 12/18/2024 | 12/19/2024 | 12/21/2024 | 12/21/2024 |  |  | OSEC-8-24-5778 | 5880000 |  | 5880000 | 5272400 |  | 5272400 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/21/2024 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 12/18/2024
24 | Procurement of Board and Lodging for the Instructional Leadership Training (ILT): Strengthening Learning Conditions for Early Literacy | [19 empty] | CLMD | NO | CB | 10/21/2024 | 10/23/2024 | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/14/2024 | 11/15/2024 | 11/18/2024 | 11/19/2024 | 11/20/2024 |  |  | OSEC-8-24-1736 | 2904500 |  | 2904500 | 2787840 |  | 2787840 | COA, NEDA, GWATCH, PPSTA, PCCI | 10/31/2024 | 11/13/2024 | 11/13/2024 | 11/13/2024 | 11/14/2024
25 | Procurement of Supplementary Learning Resources (SLRs) for Library Hubs and Delivery to Eight (8) SDOs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tacloban) FY 2023-Lot 3 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 2024-01-12 | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/24/2024 | 12/26/2024 | 12/27/2024 | 12/31/2024 |  |  | OSEC-8-23-5880 | 2551111.09 |  | 2551111.09 | 2551111.09 |  | 2551111.09 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024
26 | Procurement of Supplementary Learning Resources (SLRs) for Library Hubs and Delivery to Eight (8) SDOs (Biliran, E. Samar, Leyte, No. Samar, Ormoc, Samar, So. Leyte, Tacloban) FY 2023-Lot 2 | [19 empty] | CLMD-LRMS | NO | CB | 5/13/2024 | 2024-01-12 | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/24/2024 | 12/26/2024 | 12/27/2024 | 12/31/2024 |  |  | OSEC-8-23-5645 | 420502 |  | 420502 | 420502 |  | 420502 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-09-12 | 12/23/2024 | 12/23/2024 | 12/23/2024 | 12/23/2024
27 | Procurement for Emergency GO Bag Sets for DepEd Regional Office VIII Personnel | [19 empty] | ESSD | NO | CB | 2024-10-12 | 2024-03-12 | 2024-10-12 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/26/2024 | 12/27/2027 | 12/28/2024 | 12/31/2024 |  |  | OSEC-8-23-5645 | 2231515 |  | 2231515 | 1972838 |  | 1972838 | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-12 | 12/24/2024 | 12/24/2024 | 12/24/2024 | 12/24/2024
[33 empty] | Total Allotted Budget of Procurement Activities |  |  |  |  | 290693500.62 |  | 290693500.62
[33 empty] | Total Contract Price of Procurement Activities Conducted | [7 empty] | 206232574.12 |  | 206232574.12
[33 empty] | Total Savings (Total Allotted Budget - Total Contract Price) |  |  |  |  | 84460926.5
ON-GOING PROCUREMENT ACTIVITIES
1 | Procurement for the Hiring of a Licensed Security Agency to Provide Nine (9) Security Guards for Twelve (12) Months from April 2025 to March 2026 (EARLY PROCUREMENT ACTIVITY) | [19 empty] | ADMIN | YES | CB | 9/30/2024 | 2024-02-10 | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 2024-06-11 | 11/16/2024 | [5 empty] | RO GASS FUND | 2381147.25 | 104923000 |  | 2340274.68 | 2340274.68 |  | COA, NEDA, GWATCH, PPSTA, PCCI | 2024-10-10 | 10/23/2024 | 10/23/2024 | 10/23/2024 | 2024-06-11
2 | Production and Delivery of Grades 6 and 10 Q1 and Q2 SLMs to 13 SDOs (EARLY PROCUREMENT ACTIVITY) | [19 empty] | CLMD-LRMS | YES | AGENCY TO AGENCY | 9/30/2024 | N/A | N/A | N/A | N/A | N/A | N/A | 11/26/2024 | [5 empty] | FY 2025 Directly Released Funds | 106537200 |  | 106537200 | 104923000 |  | 104923000 | COA, NEDA, GWATCH, PPSTA, PCCI | N/A | N/A | N/A | N/A | N/A
3
Total Alloted Budget of On-going Procurement Activities | [38 empty] | 104923000 | 106537200 | 107263274.68 | 2340274.68 | 104923000
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by:
[21 empty] | RACHEL R. CUEVAS | [10 empty] | HARVIE D. VILLAMOR | [10 empty] | EVELYN R. FETALVERO, CESO III
[21 empty] | Head, BAC Secretariat | [10 empty] | Chief, HRDD | [10 empty] | Regional Director
[32 empty] | Chairperson- BAC | [8 empty] | Head of the Procuring Entity (HoPE)

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement